## Summary
Summary of Estimation
| Total | Estimated | Unit
| Team Size | 0 | Members
| Effort | 50 | Man-day
| Cost | 400 | USD
| Cost After Discounted | 400 | 400
| * Discount Percentage: | 0%
* Note:

## Effort Estimate
Effort Estimation
| (1) | Development effort: |  | 50
| (2) | Project Management effort: |  | 0
| Total = (1) + (2) |  |  | 50
| Note: Unit of effort is applying to estimate is: |  |  | man-day
Development Effort
| No. | System/Subsystem /Feature | Function |  | Getting Reqs |  | HTML Design |  | Coding |  | Testing | [11 empty] | Total Effort
[5 empty] | Effort | Roles | Effort | Roles | Effort | Roles | Effort | Roles | Effort | Roles | Effort | Roles | Effort | Roles | Effort | Roles | Effort | Roles
| 1 |  | Creating Project Infrastructure
| 2 | install project
| 3 |  | - java 7 - spring 4.0.6 - spring security 3.2 - sping-data-mongoDB - MongoDB |  | 15
| 4 | Login and Logout
| 5 |  | Create login and logout function |  | 10
| 6 | Create User
| 7 |  | Create User for System base on usename(email) , password , DOB , SMS contact |  | 10
| 8 |  | Export Json data by use API restful and convert Json data to employee object (webservice + security) |  | 15
| Total Effort |  |  |  | 50 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 50
Project Management Effort
| The project management usually takes possession of |  |  |  | 10 | % on the total effort of development activities
| So, the estimated effort for management is: |  |  |  | 6.25 | (man-day)

## Staff Estimate
Staff Estimation
Acquired Staff
| No. | Roles | Abbr. | Total Effort | Quantity | Description
(man-day)
| 1 | Project Leader | PL | 0
| 2 | Developer | DEV | 6.25
| 3 | Designer | DS | 0
| 4 | Tester | QC | 0
|  |  |  | Numbers of Staff: | 0

## Cost Estimate
Cost Estimation
| (1) | Human Resources cost: | 400
| (2) | Software Resources cost: | 0
| Total = (1) + (2) |  | 400
| Note: Unit of cost is applying to estimate is: |  | USD
Human Resources Cost
| No. | Roles | Abbr. | Total Effort | Hour Rate | Cost
|  |  |  | (man-day) | (USD)
| 1 | Project Leader | PL | 0 | 0 | 0
| 2 | Developer | DEV | 6.25 | 8 | 400
| 3 | Designer | DS | 0 | 0 | 0
| 4 | Tester | QC | 0 | 0 | 0
[5 empty] | Total: | 400
Software Resources Cost
| No. | Items | Type | Number of Licences | Cost/licence | Cost
(USD)
1
[5 empty] | Total: | 0